## Лист1
WEDDING PLANNING TIMELINE 12 MONTHS |  |  |  | 1
| WHAT TO DO |  | ASSIGNED TO | START DATE | END DATE | COMMENTS
| 1 | 12 months before |  | 2019-04-01 | 2019-04-30
| 1.1 | Come up with a tentative budget and talk to your love about what your ideal wedding would look like. |  | 2019-04-01 | 2019-04-05
| 1.2 | Decide when you want to get married. If your date is flexible, check with several venues you like to see when exactly they’re available and how much they will cost. |  | 2019-04-06 | 2019-04-09
| 1.3 | Research venues |  | 2019-04-10 | 2019-04-17
| 1.4 | Draft a guest list |  | 2019-04-18 | 2019-04-21
| 1.5 | Talk to your parents about their ability to contribute and finalize your wedding budget. |  | 2019-04-22 | 2019-04-23
| 1.6 | If you’ve decided to hire a wedding planner, interview and select yours. |  | 2019-04-24 | 2019-04-30
| 2 | 10-11 months before |  | 2019-05-01 | 2019-06-30
| 2.1 | Book your ceremony and reception venues. |  | 2019-05-01 | 2019-05-07
| 2.2 | Choose your wedding party. |  | 2019-05-08 | 2019-05-15
| 2.3 | Book an officiant. |  | 2019-05-16 | 2019-05-20
| 2.4 | Find and order your wedding gown. |  | 2019-05-21 | 2019-05-26
| 2.5 | Start interviewing wedding vendors and professionals (florist, stationer, DJ/musician, band, videographer, etc.). |  | 2019-05-27 | 2019-06-01
| 2.6 | Plot out the decor scheme for your wedding. Consider any rentals you’ll need to execute your vision. |  | 2019-06-01 | 2019-06-06
| 2.7 | Meet with caterers; sample and choose reception food. |  | 2019-06-07 | 2019-06-13
| 2.8 | Book your wedding photographer. |  | 2019-06-14 | 2019-06-19
| 2.9 | Take engagement photos. |  | 2019-06-20 | 2019-06-25
| 2.10 | Send out save-the-dates for a destination wedding. |  | 2019-06-26 | 2019-06-30
| 3 | 8-9 months before |  | 2019-07-01 | 2019-08-31
| 3.1 | Finalize bar service. |  | 2019-07-01 | 2019-07-10
| 3.2 | Register for gifts. |  | 2019-07-11 | 2019-07-15
| 3.3 | Reserve any necessary rentals. |  | 2019-07-16 | 2019-07-23
| 3.4 | Reserve room blocks for out-of-town guests. |  | 2019-07-24 | 2019-07-27
| 3.5 | Book wedding band/DJ. |  | 2019-07-28 | 2019-08-07
| 3.6 | Book florist. |  | 2019-08-08 | 2019-08-15
| 3.7 | Finalize stationery suite. |  | 2019-08-15 | 2019-08-31
| 4 | 6-7 months before |  | 2019-09-01 | 2019-10-31
| 4.1 | Set up your wedding website. |  | 2019-09-01 | 2019-10-31
| 4.2 | Order bridesmaid dresses. |  | 2019-09-01 | 2019-10-31
| 4.3 | Send save-the-dates. |  | 2019-09-01 | 2019-10-31
| 4.4 | Finalize wedding entertainment. |  | 2019-09-01 | 2019-10-31
| 4.5 | Order formalwear for the groom. |  | 2019-09-01 | 2019-10-31
| 4.6 | Start researching honeymoon travel. |  | 2019-09-01 | 2019-10-31
| 5 | 4-5 months before |  | 2019-11-01 | 2019-12-31
| 5.1 | Purchase wedding rings. |  | 2019-11-01 | 2019-11-10
| 5.2 | Order invitations. |  | 2019-11-11 | 2019-11-16
| 5.3 | Order formalwear for groomsmen. |  | 2019-11-17 | 2019-11-23
| 5.4 | Attend cake tastings; choose a baker and cake. |  | 2019-11-24 | 2019-11-30
| 5.5 | Choose attire for flower girl/ring bearer. |  | 2019-12-01 | 2019-12-10
| 5.6 | Finalize ceremony order; ask friends to do readings. |  | 2019-12-11 | 2019-12-17
| 5.7 | Book honeymoon. |  | 2019-12-17 | 2019-12-31
| 6 | 3 months before |  | 2020-01-01 | 2020-01-31
| 6.1 | Hire calligrapher for invitations (if necessary). |  | 2020-01-01 | 2020-01-07
| 6.2 | Have a wedding shower. |  | 2020-01-08 | 2020-01-15
| 6.3 | Book venue for rehearsal dinner. |  | 2020-01-16 | 2020-01-23
| 6.4 | Purchase accessories, including jewelry, shoes, veil, cuff links, bow ties, etc. |  | 2020-01-24 | 2020-01-31
| 7 | 2 months before |  | 2020-02-01 | 2020-02-28
| 7.1 | Mail your invitations. |  | 2020-02-01 | 2020-02-05
| 7.2 | Meet and book stylists/makeup artists and test out wedding hairstyles and makeup looks. |  | 2020-02-06 | 2020-02-13
| 7.3 | Purchase gifts for your wedding party. |  | 2020-02-14 | 2020-02-18
| 7.4 | Order wedding programs. |  | 2020-02-19 | 2020-02-21
| 7.5 | Write or choose your wedding vows. |  | 2020-02-22 | 2020-02-25
| 7.6 | Book any necessary day-of transportation. |  | 2020-02-26 | 2020-02-28
| 8 | 1 month before |  | 2020-03-01 | 2020-03-31
| 8.1 | Confirm playlist/do-not-play list with musicians or DJ. |  | 2020-03-01 | 2020-03-03
| 8.2 | Send rehearsal dinner invites. |  | 2020-03-04 | 2020-03-07
| 8.3 | Purchase wedding favors. |  | 2020-03-08 | 2020-03-11
| 8.4 | Wrap up DIY projects. |  | 2020-03-12 | 2020-03-16
| 8.5 | Have a final gown fitting; ensure your maid of honor knows how to bustle your gown, if necessary. |  | 2020-03-17 | 2020-03-19
| 8.6 | Apply for your marriage license. |  | 2020-03-20 | 2020-03-22
| 8.7 | Create welcome bags for out-of-town guests. |  | 2020-03-23 | 2020-03-26
| 8.8 | Confirm all day-of details with vendors; make any necessary substitutions/changes. |  | 2020-03-27 | 2020-03-28
| 8.9 | Confirm all important details with wedding party members (e.g. arrival times, attire fittings, etc.). |  | 2020-03-29 | 2020-03-30
| 8.10 | Confirm that necessary space for all vendors and equipment is available at the venue. |  | 2020-03-29 | 2020-03-30
| 8.11 | Arrange for care of pets/home during your honeymoon. |  | 2020-03-29 | 2020-03-30
| 8.12 | Have bachelor/bachelorette parties. |  | 2020-03-30 | 2020-03-31
| 9 | 3 weeks before |  | 2020-03-08 | 2020-03-31
| 9.1 | Contact any MIA guests to get their RSVPs. |  | 2020-03-08 | 2020-03-10
| 9.2 | Finalize guest list and give head count to caterer/venue. |  | 2020-03-11 | 2020-03-14
| 9.3 | Confirm vendor meals with caterer. |  | 2020-03-15 | 2020-03-22
| 9.4 | Prepare must-have shot list with photographer; give names of all VIPs. |  | 2020-03-23 | 2020-03-31
| 10 | 2 weeks before |  | 2020-03-15 | 2020-03-31
| 10.1 | Get final haircut and color. |  | 2020-03-15 | 2020-03-18
| 10.2 | Confirm all honeymoon travel. |  | 2020-03-19 | 2020-03-23
| 10.3 | Plan reception seating chart. |  | 2020-03-24 | 2020-03-31
| 11 | 1 week before |  | 2020-03-22 | 2020-03-31
| 11.1 | Print or DIY your escort cards. |  | 2020-03-22 | 2020-03-24
| 11.2 | Call all vendors and confirm delivery/setup/takedown arrangements. |  | 2020-03-25 | 2020-03-27
| 11.3 | Give your day’s schedule to ceremony/reception site managers, including deliveries, setup, takedown, etc. |  | 2020-03-28 | 2020-03-31
| 12 | 2-3 days before |  | 2020-03-29 | 2020-03-31
| 12.1 | Make sure your dress is ready to go; get it steamed or pressed if necessary. |  | 2020-03-29 | 2020-03-31
| 12.2 | Pick up the mens’ formalwear. |  | 2020-03-29 | 2020-03-31
| 12.3 | Finalize bridal party positions and order they’ll walk down the aisle. |  | 2020-03-29 | 2020-03-31
| 12.4 | Deliver place cards, programs, menus, etc. to appropriate venue or site managers. |  | 2020-03-29 | 2020-03-31
| 12.5 | Drop off welcome bags at guest hotels and give delivery instructions to the front desk. |  | 2020-03-29 | 2020-03-31
| 12.6 | Designate someone as the emergency contact person and give out their phone number to all vendors. Make sure to pick a trusted relative or responsible member of the bridal party. |  | 2020-03-29 | 2020-03-31
| 12.7 | Rehearse ceremony at venue. |  | 2020-03-29 | 2020-03-31
| 12.8 | Write final checks to vendors and professionals. |  | 2020-03-01 | 2020-03-31
| 13 | 1 day before |  | 2020-03-31 | 2020-03-31
| 13.1 | Attend rehearsal dinner. |  | 2020-03-31 | 2020-03-31
| 13.2 | Give gifts to attendants. |  | 2020-03-31 | 2020-03-31
| 13.3 | Give marriage license to officiant. |  | 2020-03-31 | 2020-03-31
| 13.4 | Print out your vows if you’re writing your own. |  | 2020-03-31 | 2020-03-31
| 13.5 | Get a mani and pedi. |  | 2020-03-31 | 2020-03-31
| 14 | On the BIG DAY |  | 2020-04-01 | 2020-04-01
| 14.1 | Eat something hearty for breakfast! |  | 2020-04-01 | 2020-04-01
| 14.2 | Give wedding rings to a member of the bridal party for safe keeping. |  | 2020-04-01 | 2020-04-01
| 14.3 | Introduce your vendors and site managers to your emergency contact. |  | 2020-04-01 | 2020-04-01
| 14.4 | Ensure final checks, including tips, are in envelopes and ready to be handed off to vendors and professionals. |  | 2020-04-01 | 2020-04-01
| 14.5 | Eat, drink, and be married! |  | 2020-04-01 | 2020-04-01
| 15 | In the weeks after the wedding |  | 2020-04-02 | 2020-04-21
| 15.1 | Send thank-you notes. |  | 2020-04-02 | 2020-04-04
| 15.2 | Return any remaining rentals. |  | 2020-04-04 | 2020-04-06
| 15.3 | Have your gown cleaned and/or preserved. |  | 2020-04-04 | 2020-04-06
| 15.4 | Return formalwear. |  | 2020-04-04 | 2020-04-06
| 15.5 | Enjoy your honeymoon! |  | 2020-04-04 | 2020-04-21
| 15.6 | Change your last name. |  | 2020-04-04 | 2020-04-21
| 15.7 | Order your wedding album. |  | 2020-04-17 | 2020-04-21